INVERSE PROBLEM FOR LIGHT SPREADING APPLIED TO MEDICAL TOMOGRAPHY

Project Report Version 1

Desmond Roussel Ngueguin

**Under de supervision of**

Emmanuel Franck, Laurent Navoret, and Vincent Vigon

Sommaire

[I. CONTEXT 2](#_Toc40659949)

[II. OBJECTIVES 2](#_Toc40659950)

[III. ROADMAP AND DEADLINES 3](#_Toc40659951)

[1. Phase 1: Solving the PDE with Finite Volumes 3](#_Toc40659952)

[a. Step 1: The equilibrium part 3](#_Toc40659953)

[b. Step 2: Solving the rest 4](#_Toc40659954)

[2. Phase 2: Descriptive statistics 5](#_Toc40659955)

[a. Step 1: Data analysis 5](#_Toc40659956)

[b. Step 2: Finding the density 5](#_Toc40659957)

[c. Step 3: The absorption and scattering opacities 5](#_Toc40659958)

[IV. RESSOURCES AND BUDGET 5](#_Toc40659959)

[1. Phase 1: Solving the PDE 6](#_Toc40659960)

[2. Phase 2: Descriptive statistics 6](#_Toc40659961)

[V. MILESTONES 6](#_Toc40659962)

[VI. DELIVRABLES AND OUTCOME 8](#_Toc40659963)

[VII. REFERENCES 9](#_Toc40659964)

# 

# CONTEXT

Inverse problems are some of the most important problems in science and mathematics because of their wide range of applications in medical imaging, computer vision, radar, etc. These are problems that, given a set of observations, tell us the parameters that cause them, parameters that we cannot directly observe. In general, numerically solving an inverse problem requires advanced optimization algorithms. However, those can be difficult to implement. That is why we are introducing an approach based on machine learning and neural networks.

The problem to solve is a medical tomography inverse problem by infrared. This project will prepare to study a neural network-based method for finding the optical properties of an organ. The project was suggested and is run by the MOCO (“Modélisation et Contrôle”) team at IRMA (“Institut de Recherche Mathématique Avancée”). This team is made up of specialists in PDE analysis, control theory, high-performance scientific computing, and statistics (IRMA, n.d.). This specific project is under the guidance of IRMA researchers Emmanuel Franck, Laurent Navoret, and Vincent Vigon.

# OBJECTIVES

The **main objective** of this project is to understand how the optical properties of an organ affect a signal traveling through it. We send an infrared light beam through an organ and we measure the signal on part of that organ. Knowing the initial conditions and the signal at all times, we can infer the influence of the organ’s properties. Namely the influence of the density, the scattering opacity, and the absorption opacity.

The project is divided into two parts. First, we must solve the partial differential equation (PDE) for a simplified version of the **radiative transfer equation** (1) in 1D. This will count as our **1st specific objective**. The **2nd specific objective** will aim to understand the data emanating from the 1st part. In this part, we will measure the signal’s value on the boundaries of a domain at all times (or the complete signal at the end of the simulations), then we will seek to understand the influence of the domain’s properties on the signal.

(1)

Where:

* is the Stefan-Boltzmann constant
* is the thermal capacity of the medium
* is the speed of light
* is the temperature of the medium
* is the energy of the photons
* is the flux of the photons
* is the density of the medium
* is the absorption opacity
* is the scattering opacity

We should note that when the scattering opacity and the absorption opacity are high enough to be close to the speed of light (which is far larger than the observed phenomenon’s speed), the model in (1) is reduced to the following:

This model is called the **diffusion approximation** (Franck, 2020, p.7)**.** It matches a diffusion equation with a diffusion coefficient of . But more importantly, it gives us a good way of testing our program.

# ROADMAP AND DEADLINES

## Phase 1: Solving the PDE with Finite Volumes

Due to the hyperbolic nature of the PDE (1)*,* the constraints of our domain, and the need to deal with discontinuities, the **finite volumes** method is well suited to solving it. However, the well-known Rusanov scheme is not accurate enough, especially when the opacities are very high. Therefore, we will use a finite volume scheme with a splitting strategy (Franck, 2012, p. 160).

First, we must discretize our domain to form a mesh. Let and be the two real numbers such that , and an integer. We split the domain into cells of equal length to obtain a uniform mesh. At the two edges, we add two “ghost” cells. In total, we have cells. Let’s denote by the length of the intervals (the volume of the cells). For each cell , we write its center, its left edge, and its right edge.

Next, we write the splitting scheme. Two steps are required here.

### Step 1: The equilibrium part

We consider the “equilibrium” part of (1). That is, the photons are not moving, and we only take into account the relaxation terms in temperature (Franck, 2012, p. 160). This leads to all the terms with in (1) to be equal to . The equation becomes:

Writing , we solve (3 on each independent cell. The numerical scheme is given below.

Rewritten as:

Applying Cramer’s rule, we get:

Where

* , and are the value values of , and on the cell at the beginning of the step.
* , , , and
* written above is a function of and . Thus, it is actually .
* is such that

Since this step is a fixed point method, we iterate on until we get close enough to the fixed point , or more precisely . We then move to the next step.

### Step 2: Solving the rest

Once the first step converges, we move to this step with the values of and on each cell updated. We write:

With

We must also include the CFL condition below to ensure the scheme’s stability.

We can rewrite (5 as:

With

and

Once all of this is done, we move back to step 1, then back to step 2 and so on until we reach a predefined time at which we want the solution.

## Phase 2: Descriptive statistics

### Step 1: Data analysis

After exporting the data from simulations in the previous step, we will need to study them using appropriate descriptive statistics tools. We will then have to find meaningful correlations between the variables. During this step, we will try to show the results that the neural network will later find by itself. The step will serve as a preparation for the AI training and predicting phase, to be completed during the internship.

### Step 2: Finding the density

Here we will make the AI understand the trends we found in the previous step. Knowing not only the signals and at all times, but also the scattering and absorption opacities ( and ), we will rebuild the domain’s density . We can see that the inputs for the neural network will be 2D tensors (indexed by and ) while the output will be 1D (indexed only by ).

First, we will train and validate the neural network with the data obtained from solving the PDE (1) in the first phase. Second, we will test it hoping it generalizes well.

### Step 3: The absorption and scattering opacities

This step is quite similar to the previous step with the only difference that we will be trying to predict and knowing this time. However, it requires a more complex neural network.

Just as the previous step, this part is no longer part of the project, we will cover it during the internship.

# RESSOURCES AND BUDGET

Considerable resources are needed to complete this project. For computing purposes, a server on Atlas is available at <v100.math.unistra.fr>. Extra computing resources are also allocated through [Google Colab](https://colab.research.google.com/notebooks/welcome.ipynb).

## Phase 1: Solving the PDE

This part will be almost entirely coded in C++. We will need the [Eigen](http://eigen.tuxfamily.org/index.php?title=Main_Page) library for vector operations. A function parser like [cparse](https://github.com/cparse/cparse/wiki/Getting-Started) could also be useful. The output files will be exported in the CSV format for visualization with Matplotlib in Python.

## Phase 2: Descriptive statistics

Since Python is the language of choice for data science, we will use it during this phase. For this to work, we will have to find a way of storing all the data from our PDE simulations in their 2D shapes, all this in one single file. We will then load the data and study it using the software library for data manipulation and analysis called Pandas.

# MILESTONES CHECK

This section gives a summary for the roadmap, the objectives and the deadlines for the project.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Milestone | | Details | Tools needed | Deadline | Estimated number of hours | Actual number of hours |
| Understanding the model | | We will seek to understand the PDE (1) and its numerical model on a slightly theoretical basis. This has already been done, but new information keeps coming every day. |  | April 2, 2020 | 8 hours |  |
| Report version 0 | | A report indicating the context and the roadmap for the project. This milestone is currently under completion. | Microsoft Office Word | April 15, 2020 | 16 hours |  |
| Phase 1: Finite Volumes | Solving the scheme | Using the finite volumes method in 1D, we need to solve the PDE (1). This has milestone has already been completed. | VS Code, GitHub,  Eigen, Cparse | April 15, 2020 | 40 hours |  |
| Verification | Verify that the finite volume method is correctly implemented and solves a direct problem on a given domain. A good way to verify our splitting scheme is to test it on the diffusion approximation in (2. Tests will be put in place for continuous integration. We will need to find and correct all the bugs that appear in the code. | VS Code  Matplotlib | April 29, 2020 | 16 hours |  |
| Benchmarking | Compare our algorithm to known solutions in order to optimize our code for speed. This step might be done multiple times depending on the changes we make to the algorithm during verification. | VS Code | April 29, 2020 | 4 hours |  |
| Validation | Making sure the problem solves the correct direct problems linked to medical tomography. | VS Code, Matplotlib | April 29, 2020 | 4 hours |  |
| Data export | Writing and running a script that exports thousands of instances of a correctly solved direct problem. We will make sure to export the data one state of the model at a time. This requires us to run the above-optimized program a great number of times, which is the reason we need to get it right on the first try. | Altas | May 5, 2020 | 8 hours |  |
| Phase 2: Descriptive statistics | Studying the data | Using the exported data, we will seek to learn new information, finding interesting correlations, creating new variables, deleting outliers, cleaning out the data, and so on. During the internship, our goal will be to make the AI understand these correlations. | Pandas | May 19, 2020 | 24 hours |  |
| Verification | Verify that the model is properly studied. A positive indicator might be that when generating new instances of the data, we continue seeing the same trends. | Google Colab | May 19, 2020 | 16 hours |  |
| Validation | Check that the trends we find are effectively the trends from light spreading in medical tomography. We will compare our data trends to known databases in the same area of study. | Google Colab | May 19, 2020 | 4 hours |  |
| Benchmarking | Check that our algorithms for analysis are fast enough to be easily repeatable on other systems. | Google Colab | May 19, 2020 | 4 hours |  |
| Report version 1 | | The task is to write a more complete version of the report. | MS Word | May 19, 2020 | 8 hours |  |
| Report version 2 | | The final version of the report, incorporating corrections indicated by the supervisors. | MS Word | May 19, 2020 | 4 hours |  |
| Presentation | | A slideshow to be written in PowerPoint. | MS PowerPoint | May 19, 2020 | 8 hours |  |

This represents **164 hours** (approximately 7 full days) working on the project. Of course, these are just estimations and they will be appropriately adjusted in the following weeks to better fit the reality.

# DELIVRABLES AND OUTCOME

What was be delivered at the end of this project are:

* A software names ***transfer*** that can model light spreading according to the PDE (1)
* A notebook that analyses meaningful trends in the data generated by ***transfer.***
* A typewritten report named **rapport\_v1.pdf**
* A powerpoint presentation named **presentation.pdf (***yet to be completed***)**

All these files can be found on the GitHub repository [feelpp/csmi-m1-2020-moco-inverse](https://github.com/feelpp/csmi-m1-2020-moco-inverse) along with instructions on how to run the software.

# REFERENCES

* Franck, E. April 1, 2020. *“Projets de M1”.* Personal notes from Emmanuel Franck summarizing the guidelines for the project.
* Franck, E. October 23, 2012. *“Construction et analyse numérique de schéma asymptotic preserving sur maillages non structurés. Application au transport linéaire et aux systèmes de Friedrichs”*. Retrieved from <https://tel.archives-ouvertes.fr/file/index/docid/744371/filename/theseFranckv3.pdf>
* IRMA. (n.d.). *“Institut de Recherche Mathématique Avancée, UMR 7501"*. Retrieved from <http://irma.math.unistra.fr/rubrique162.html>